## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes | budget | approved extra cost | progress
1 | Yes | Auto Scheduled | Contracts | 0 days | 01 June 2008 08:00 | 01 June 2008 08:00 |  | 1
2 | Yes | Auto Scheduled | Supply Lot Sale Agreement | 0 days | 01 June 2008 08:00 | 01 June 2008 08:00 |  | 2
3 | Yes | Auto Scheduled | Supply Construction Agreement | 0 days | 01 June 2008 08:00 | 01 June 2008 08:00 |  | 2
4 | Yes | Auto Scheduled | Supply Contract Plans | 0 days | 01 June 2008 08:00 | 01 June 2008 08:00 | 3 | 2
5 | Yes | Auto Scheduled | Supply Contract Specifications | 0 days | 01 June 2008 08:00 | 01 June 2008 08:00 | 3 | 2
6 | Yes | Auto Scheduled | Supply Contract Site Plan | 0 days | 01 June 2008 08:00 | 01 June 2008 08:00 | 3 | 2
7 | Yes | Auto Scheduled | Secure Financing | 0 days | 01 June 2008 08:00 | 01 June 2008 08:00 |  | 2
8 | Yes | Auto Scheduled | Construction Loan Settlement | 0 days | 01 June 2008 08:00 | 01 June 2008 08:00 |  | 2
9 | Yes | Auto Scheduled | Document Review & Revision | 25 days | 02 June 2008 08:00 | 04 July 2008 17:00 |  | 1
10 | Yes | Auto Scheduled | Review & Finalize Plans | 15 days | 02 June 2008 08:00 | 20 June 2008 17:00 | 4 | 2
11 | Yes | Auto Scheduled | Review & Finalize Specifications | 20 days | 02 June 2008 08:00 | 27 June 2008 17:00 | 5 | 2
12 | Yes | Auto Scheduled | Review & Finalize Site Plan | 1 day | 23 June 2008 08:00 | 23 June 2008 17:00 | 6,10 | 2
13 | Yes | Auto Scheduled | Print Construction Drawings | 5 days | 30 June 2008 08:00 | 04 July 2008 17:00 | 10,11,12 | 2
14 | Yes | Auto Scheduled | Approve Revised Plans | 0 days | 04 July 2008 17:00 | 04 July 2008 17:00 | 13 | 2
15 | Yes | Auto Scheduled | Approve Revised Specifications | 0 days | 04 July 2008 17:00 | 04 July 2008 17:00 | 13 | 2
16 | Yes | Auto Scheduled | Approve Revised Site Plan | 0 days | 04 July 2008 17:00 | 04 July 2008 17:00 | 13 | 2
17 | Yes | Auto Scheduled | Bids & Contracts | 24 days | 07 July 2008 08:00 | 07 August 2008 17:00 |  | 1
18 | Yes | Auto Scheduled | Make Copies of Plans | 3 days | 07 July 2008 08:00 | 09 July 2008 17:00 | 14 | 2
19 | Yes | Auto Scheduled | Make Copies of Specifications | 2 days | 07 July 2008 08:00 | 08 July 2008 17:00 | 15 | 2
20 | Yes | Auto Scheduled | Distribute Plans & Specifications | 1 day | 10 July 2008 08:00 | 10 July 2008 17:00 | 18,19 | 2
21 | Yes | Auto Scheduled | Receive Bids | 10 days | 11 July 2008 08:00 | 24 July 2008 17:00 | 20 | 2
22 | Yes | Auto Scheduled | Review Bids | 5 days | 25 July 2008 08:00 | 31 July 2008 17:00 |  | 2
23 | Yes | Auto Scheduled | Sales | 5 days | 25 July 2008 08:00 | 31 July 2008 17:00 | 21 | 3
24 | Yes | Auto Scheduled | Construction | 5 days | 25 July 2008 08:00 | 31 July 2008 17:00 | 21 | 3
25 | Yes | Auto Scheduled | Execute Subcontractor Agreements | 5 days | 01 August 2008 08:00 | 07 August 2008 17:00 | 23 | 2
26 | Yes | Auto Scheduled | Grading & Building Permits | 17 days | 07 July 2008 08:00 | 29 July 2008 17:00 |  | 1
27 | Yes | Auto Scheduled | Schedule lot stake-out | 1 day | 07 July 2008 08:00 | 07 July 2008 17:00 | 13 | 2
28 | Yes | Auto Scheduled | Stake lot | 1 day | 11 July 2008 08:00 | 11 July 2008 17:00 | 27FS+3d | 2
29 | Yes | Auto Scheduled | File Grading Permit Application | 1 day | 07 July 2008 08:00 | 07 July 2008 17:00 | 16 | 2
30 | Yes | Auto Scheduled | File Building Permit Application | 3 days | 07 July 2008 08:00 | 09 July 2008 17:00 | 14,15,16 | 2
31 | Yes | Auto Scheduled | Post Lot Identification | 1 day | 14 July 2008 08:00 | 14 July 2008 17:00 | 28,29,30 | 2
32 | Yes | Auto Scheduled | Meet Sediment Control Inspector | 1 day | 15 July 2008 08:00 | 15 July 2008 17:00 | 29FS+2d,28,31 | 2
33 | Yes | Auto Scheduled | Walk Lot w/ Owner | 1 day | 16 July 2008 08:00 | 16 July 2008 17:00 | 32 | 2
34 | Yes | Auto Scheduled | Install Construction Entrance | 1 day | 17 July 2008 08:00 | 17 July 2008 17:00 | 32,33 | 2
35 | Yes | Auto Scheduled | Install Sediment Controls | 2 days | 17 July 2008 08:00 | 18 July 2008 17:00 | 32,33 | 2
36 | Yes | Auto Scheduled | Sediment Control Insp. | 1 day | 21 July 2008 08:00 | 21 July 2008 17:00 | 34,35 | 2
37 | Yes | Auto Scheduled | Grading Permit Issued | 1 day | 22 July 2008 08:00 | 22 July 2008 17:00 | 36 | 2
38 | Yes | Auto Scheduled | County Permit Process | 10 days | 10 July 2008 08:00 | 23 July 2008 17:00 | 30 | 2
39 | Yes | Auto Scheduled | Building Permit Approved | 1 day | 24 July 2008 08:00 | 24 July 2008 17:00 | 38,37 | 2
40 | Yes | Auto Scheduled | Pay Permit Fees and Excise Taxes | 1 day | 29 July 2008 08:00 | 29 July 2008 17:00 | 39FS+2d | 2
41 | Yes | Auto Scheduled | Building Permit Issued | 0 days | 29 July 2008 17:00 | 29 July 2008 17:00 | 40 | 2
42 | Yes | Auto Scheduled | Site Work | 7 days | 23 July 2008 08:00 | 31 July 2008 17:00 |  | 1
43 | Yes | Auto Scheduled | Clear Lot | 3 days | 23 July 2008 08:00 | 25 July 2008 17:00 | 37 | 2
44 | Yes | Auto Scheduled | Strip Topsoil & Stockpile | 1 day | 28 July 2008 08:00 | 28 July 2008 17:00 | 43 | 2
45 | Yes | Auto Scheduled | Stake Lot for Excavation | 1 day | 28 July 2008 08:00 | 28 July 2008 17:00 | 43 | 2
46 | Yes | Auto Scheduled | Rough grade lot | 1 day | 29 July 2008 08:00 | 29 July 2008 17:00 | 43,45 | 2
47 | Yes | Auto Scheduled | Excavate for foundation | 2 days | 30 July 2008 08:00 | 31 July 2008 17:00 | 39,45,43,46 | 2
48 | Yes | Auto Scheduled | Foundation | 24 days | 01 August 2008 08:00 | 03 September 2008 17:00 |  | 1
49 | Yes | Auto Scheduled | Layout footings | 1 day | 01 August 2008 08:00 | 01 August 2008 17:00 | 47 | 2
50 | Yes | Auto Scheduled | Dig Footings & Install Reinforcing | 1 day | 04 August 2008 08:00 | 04 August 2008 17:00 | 49 | 2
51 | Yes | Auto Scheduled | Footing Inspection | 0 days | 04 August 2008 17:00 | 04 August 2008 17:00 | 50 | 2
52 | Yes | Auto Scheduled | Pour footings | 1 day | 05 August 2008 08:00 | 05 August 2008 17:00 | 51 | 2
53 | Yes | Auto Scheduled | Pin Footings | 1 day | 06 August 2008 08:00 | 06 August 2008 17:00 | 52 | 2
54 | Yes | Auto Scheduled | Stock Block, Mortar, Sand | 1 day | 07 August 2008 08:00 | 07 August 2008 17:00 | 53 | 2
55 | Yes | Auto Scheduled | Build Block Foundation | 15 days | 08 August 2008 08:00 | 28 August 2008 17:00 | 53,54 | 2
56 | Yes | Auto Scheduled | Foundation Certification | 0 days | 28 August 2008 17:00 | 28 August 2008 17:00 | 55 | 2
57 | Yes | Auto Scheduled | Draw #1 (Location Survey) | 0 days | 28 August 2008 17:00 | 28 August 2008 17:00 | 56 | 2
58 | Yes | Auto Scheduled | Fill Block Cores w/ Concrete | 1 day | 29 August 2008 08:00 | 29 August 2008 17:00 | 55 | 2
59 | Yes | Auto Scheduled | Steel Delivery | 1 day | 01 September 2008 08:00 | 01 September 2008 17:00 | 58 | 2
60 | Yes | Auto Scheduled | Set Lintels, Bolts, Cap Block | 2 days | 02 September 2008 08:00 | 03 September 2008 17:00 | 59 | 2
61 | Yes | Auto Scheduled | Lumber Delivery | 1 day | 01 September 2008 08:00 | 01 September 2008 17:00 | 58 | 2
62 | Yes | Auto Scheduled | Waterproofing and Drain Tile | 1 day | 02 September 2008 08:00 | 02 September 2008 17:00 | 61 | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | Sales Department | S | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Construction Dept. | C | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Sales Dept. | S | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Client | C | Work |  |  |  |  | 100% | $0.00/h | 0
5 | County | C | Work |  |  |  |  | 100% | $0.00/h | 0
6 | County Sediment Control Inspector | C | Work |  |  |  |  | 100% | $0.00/h | 0
7 | Sediment Control Inspector | S | Work |  |  |  |  | 100% | $0.00/h | 0
8 | Department of Permits & Licenses | D | Work |  |  |  |  | 100% | $0.00/h | 0
9 | Building Inspector | B | Work |  |  |  |  | 100% | $0.00/h | 0
10 | Mason | M | Work |  |  |  |  | 100% | $0.00/h | 0
11 | Civil Engineer | C | Work |  |  |  |  | 100% | $0.00/h | 0
12 | Concrete Subcontractor | C | Work |  |  |  |  | 100% | $0.00/h | 0
13 | Concrete Subcontractor | C | Work |  |  |  |  | 100% | $0.00/h | 0
14 | Excavation Subcontractor | E | Work |  |  |  |  | 100% | $0.00/h | 0
15 | Masonry Subcontractor | M | Work |  |  |  |  | 100% | $0.00/h | 0
16 | Block Masonry Subcontractor | B | Work |  |  |  |  | 100% | $0.00/h | 0
17 | Steel Supplier | S | Work |  |  |  |  | 100% | $0.00/h | 0
18 | Lumber Supplier | L | Work |  |  |  |  | 100% | $0.00/h | 0
19 | Waterproofing Subcontractor | W | Work |  |  |  |  | 100% | $0.00/h | 0
20 | Lender | L | Work |  |  |  |  | 100% | $0.00/h | 0
21 | Framing Subcontractor | F | Work |  |  |  |  | 100% | $0.00/h | 0
22 | Pest Control Subcontractor | P | Work |  |  |  |  | 100% | $0.00/h | 0
23 | Mechanical Subcontractor | M | Work |  |  |  |  | 100% | $0.00/h | 0
24 | Plumbing Subcontractor | P | Work |  |  |  |  | 100% | $0.00/h | 0
25 | Field Superintendent | F | Work |  |  |  |  | 100% | $0.00/h | 0
26 | Plumbing Inspector | P | Work |  |  |  |  | 100% | $0.00/h | 0
27 | Electrical Subcontractor | E | Work |  |  |  |  | 100% | $0.00/h | 0
28 | Alarm Subcontractor | A | Work |  |  |  |  | 100% | $0.00/h | 0
29 | Client's Subcontractor | C | Work |  |  |  |  | 100% | $0.00/h | 0
30 | Electrical Inspector | E | Work |  |  |  |  | 100% | $0.00/h | 0
31 | Roofing Subcontractor | R | Work |  |  |  |  | 100% | $0.00/h | 0
32 | Exterior Trim Subcontractor | E | Work |  |  |  |  | 100% | $0.00/h | 0
33 | Brick Masonry Subcontractor | B | Work |  |  |  |  | 100% | $0.00/h | 0
34 | Insulation Subcontractor | I | Work |  |  |  |  | 100% | $0.00/h | 0
35 | BGE Inspector | B | Work |  |  |  |  | 100% | $0.00/h | 0
36 | Drywall Subcontractor | D | Work |  |  |  |  | 100% | $0.00/h | 0
37 | Painting Subcontractor | P | Work |  |  |  |  | 100% | $0.00/h | 0
38 | Trim Supplier | T | Work |  |  |  |  | 100% | $0.00/h | 0
39 | Interior Trim Subcontractor | I | Work |  |  |  |  | 100% | $0.00/h | 0
40 | Cabinet Subcontractor | C | Work |  |  |  |  | 100% | $0.00/h | 0
41 | Deck Subcontractor | D | Work |  |  |  |  | 100% | $0.00/h | 0
42 | Driveway Subcontractor | D | Work |  |  |  |  | 100% | $0.00/h | 0
43 | Seeding Subcontractor | S | Work |  |  |  |  | 100% | $0.00/h | 0
44 | Hardware Subcontractor | H | Work |  |  |  |  | 100% | $0.00/h | 0
45 | Mirror Subcontractor | M | Work |  |  |  |  | 100% | $0.00/h | 0
46 | Tile Subcontractor | T | Work |  |  |  |  | 100% | $0.00/h | 0
47 | Hardwood Floor Subcontractor | H | Work |  |  |  |  | 100% | $0.00/h | 0
48 | Carpet Subcontractor | C | Work |  |  |  |  | 100% | $0.00/h | 0
49 | Department of Licensing & Permits | D | Work |  |  |  |  | 100% | $0.00/h | 0
50 | Paint Subcontractor | P | Work |  |  |  |  | 100% | $0.00/h | 0
51 | Window Cleaning Subcontractor | W | Work |  |  |  |  | 100% | $0.00/h | 0
52 | Cleaning Subcontractor | C | Work |  |  |  |  | 100% | $0.00/h | 0
53 | Superintendent | S | Work |  |  |  |  | 100% | $0.00/h | 0
54 | Builder | B | Work |  |  |  |  | 100% | $0.00/h | 0
55 | Punch Out Crew | P | Work |  |  |  |  | 100% | $0.00/h | 0
56 | Stucco Subcontractor | S | Work |  |  |  |  | 100% | $0.00/h | 0
57 | Sales Manager | S | Work |  |  |  |  | 100% | $0.00/h | 0
58 | Construction Manager | C | Work |  |  |  |  | 100% | $0.00/h | 0
59 | Project Manager | P | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Supply Lot Sale Agreement | Builder | 0 | 0d | 100%
Supply Construction Agreement | Builder | 0 | 0d | 100%
Supply Contract Plans | Builder | 0 | 0d | 100%
Supply Contract Specifications | Builder | 0 | 0d | 100%
Supply Contract Site Plan | Builder | 0 | 0d | 100%
Secure Financing | Client | 0 | 0d | 100%
Construction Loan Settlement | Client | 0 | 0d | 100%
Review & Finalize Plans | Builder | 0 | 15d | 100%
Review & Finalize Specifications | Builder | 0 | 20d | 100%
Review & Finalize Site Plan | Builder | 0 | 1d | 100%
Print Construction Drawings | Builder | 0 | 5d | 100%
Approve Revised Plans | Client | 0 | 0d | 100%
Approve Revised Specifications | Client | 0 | 0d | 100%
Approve Revised Site Plan | Client | 0 | 0d | 100%
Make Copies of Plans | Builder | 0 | 3d | 100%
Make Copies of Specifications | Builder | 0 | 2d | 100%
Distribute Plans & Specifications | Builder | 0 | 1d | 100%
Receive Bids | Builder | 0 | 10d | 100%
Sales | Builder | 0 | 5d | 100%
Construction | Builder | 0 | 5d | 100%
Execute Subcontractor Agreements | Builder | 0 | 5d | 100%
Schedule lot stake-out | Builder | 0 | 1d | 100%
Stake lot | Civil Engineer | 0 | 1d | 100%
File Grading Permit Application | Builder | 0 | 1d | 100%
File Building Permit Application | Builder | 0 | 3d | 100%
Post Lot Identification | Builder | 0 | 1d | 100%
Meet Sediment Control Inspector | Builder | 0 | 1d | 100%
Walk Lot w/ Owner | Builder | 0 | 1d | 100%
Install Construction Entrance | Excavation Subcontractor | 0 | 1d | 100%
Install Sediment Controls | Excavation Subcontractor | 0 | 2d | 100%
Sediment Control Insp. | Sediment Control Inspector | 0 | 1d | 100%
Grading Permit Issued | Sediment Control Inspector | 0 | 1d | 100%
County Permit Process | Department of Permits & Licenses | 0 | 10d | 100%
Building Permit Approved | Department of Permits & Licenses | 0 | 1d | 100%
Pay Permit Fees and Excise Taxes | Builder | 0 | 1d | 100%
Building Permit Issued | Department of Permits & Licenses | 0 | 0d | 100%
Clear Lot | Excavation Subcontractor | 0 | 3d | 100%
Strip Topsoil & Stockpile | Excavation Subcontractor | 0 | 1d | 100%
Stake Lot for Excavation | Civil Engineer | 0 | 1d | 100%
Rough grade lot | Excavation Subcontractor | 0 | 1d | 100%
Excavate for foundation | Excavation Subcontractor | 0 | 2d | 100%
Layout footings | Concrete Subcontractor | 0 | 1d | 100%
Dig Footings & Install Reinforcing | Concrete Subcontractor | 0 | 1d | 100%
Footing Inspection | Building Inspector | 0 | 0d | 100%
Pour footings | Concrete Subcontractor | 0 | 1d | 100%
Pin Footings | Civil Engineer | 0 | 1d | 100%
Stock Block, Mortar, Sand | Block Masonry Subcontractor | 0 | 1d | 100%
Build Block Foundation | Block Masonry Subcontractor | 0 | 15d | 100%
Foundation Certification | Civil Engineer | 0 | 0d | 100%
Draw #1 (Location Survey) | Lender | 0 | 0d | 100%
Fill Block Cores w/ Concrete | Block Masonry Subcontractor | 0 | 1d | 100%
Steel Delivery | Steel Supplier | 0 | 1d | 100%
Set Lintels, Bolts, Cap Block | Block Masonry Subcontractor | 0 | 2d | 100%
Lumber Delivery | Lumber Supplier | 0 | 1d | 100%
Waterproofing and Drain Tile | Waterproofing Subcontractor | 0 | 1d | 100%