## 90 degrees week 24 budget
week 26
90 degrees Apartments Embakasi on L.R. No. NAIROBI/BLOCK 97/352
PROJECT INFORMATION
Total Contract Sum |  |  | : Ksh. 60,000,000
Contract Start Date |  |  | :November, 2017
Contract Completion Date |  |  | :November, 2018
Site Handover |  |  | :December, 2018
Contract Period |  |  | :53 Calendar Weeks
by |  |  |  | bore
Lead |  |  |  | Action points
main BLOCK WEEK 26 (3RD - 9TH JUNE 2018) WORKS
Mon | REINFOCEMENT 5FLR SLAB
Tue | REINFOCEMENT 5FLR SLAB
Wed | ELECTRICAL AND MECHANICAL POINTING
Thur | ELECTRICAL AND MECHANICAL POINTING
Fri | ELECTRICAL AND MECHANICAL POINTING
Sat | 5TH FLOOR SLAB CONCRETING
main BLOCK WEEK 25 Materials on site_06TH June 2018 NOT UPDATED
|  |  | unit | quantity | rate | cost
cement |  |  | pcs | 0 | 580 | 0
ballast |  |  | tonnes | 0 | 1800 | 0
sand+Rock sand |  |  | tonnes | 0 | 2000 | 0
Reinforcement |  |  |  | 0
| D8 |  | pcs | 0 | 390 | 0
| D10 |  | pcs | 0 | 600 | 0
| D12 |  | pcs | 0 | 830 | 0
| D16 |  | pcs | 0 | 1510 | 0
| D20 |  | pcs | 0 | 2500 | 0
| D25 |  | pcs | 0 | 3700 | 0
binding wire |  |  | pcs | 0 | 2000 | 0
hoop iron |  |  | pcs | 0 | 3000 | 0
quarry stones 9x9 |  |  | Ft | 0 | 47 | 0
quarry stones 4x9 |  |  | Ft | 0 | 47 | 0
timber |  |  | item | 0 |  | 0
Nails | Roofing |  | kg | 0 | 180 | 0
| 2" |  | kg | 0 | 180 | 0
| 3" |  | kg | 0 | 180 | 0
| 4" |  | kg | 0 | 180 | 0
Marine board |  |  |  | 0 | 2800 | 0
4x2 cypress |  |  |  | 0 | 40 | 0
poles |  |  | pcs | 0 | 180 | 0
blades |  |  | pcs | 0 | 100 | 0
Mechanical |  |  | item | 0 | 0 | 0
Electrical |  |  | item | 0 |  | 0
0
main BLOCK WEEK 25 Undelivered Materials
[5 empty] | unit | Quantity | rate | Amount
1 | [7 empty] | 0
2 | [7 empty] | 0
3 | [7 empty] | 0
4 | [7 empty] | 0
5 | [7 empty] | 0
6 | [7 empty] | 0
7 | [7 empty] | 0
8 | [7 empty] | 0
0
main BLOCK WEEK 26 Schedule
ITEM |  |  | Description |  | Unit | Quantity | Rate | Cost
1 | cement |  |  |  | bags | 200 | 570 | 114000
2 | sand |  |  |  | tonnes | 0 | 1700 | 0
3 | ballast |  |  |  | tonnes | 0 | 1800 | 0
4 | Reinforcement
size
| D8 |  |  |  | pcs | 55 | 390 | 21450
| D10 |  |  |  | pcs | 0 | 600 | 0
| D12 |  |  |  | pcs | 38 | 830 | 31540
| D16 |  |  |  | pcs | 36 | 1510 | 54360
| D20 |  |  |  | pcs | 5 | 2500 | 12500
| D25 |  |  |  | pcs | 0 | 3700 | 0
5 | petrol |  |  |  | Litres | 0 | 100 | 0
6 | Nails 3kg |  |  |  | 3kg | 0 | 130 | 0
| 4kg |  |  |  | 4kg | 0 | 130 | 0
7 | Marine boards |  |  |  | pcs | 0 | 2650 | 0
8 | mould oil |  |  |  | item | 0 | 5000 | 0
9 | binding wire |  |  |  | pcs | 0 | 3000 | 0
10 | cutting blades |  |  |  | pcs | 0 | 100 | 0
11 | Plumbing materials POINTING GF |  |  |  | item | 0 |  | 0
12 | Electrical materials POINTING GF |  |  |  | item | 0 |  | 0
13 | Plumbing materials PIPING GF |  |  |  | item (approx.) | 0 |  | 0
14 | Electrical materials PIPING GF |  |  |  | item (approx.) | 0 |  | 0
15 | Brc A142 |  |  |  | pcs | 0
16 | Dpc (heavy gauge) |  |  |  | pcs 75M | 0 | 2800 | 0
17 | Antitermite. |  |  |  | pcs | 0 | 1000 | 0
18 | Lime |  |  |  | bags | 20 | 2000 | 40000
19 | Masonry stones 100mm |  |  |  | ft | 1200 | 47 | 56400
20 | Masonry stones 200mm |  |  |  | ft | 3600 | 47 | 169200
21 | HARDCORE |  |  |  | cm | 0 |  | 0
22 | mild steel |  |  |  | item |  |  | 10000
23 | [5 empty] | 0 |  | 0
24 | [5 empty] | 0 |  | 0
25 | [5 empty] | 0 |  | 0
509450
main BLOCK WEEK 26 sub-contracting
ITEM | Description
a | Main contractor payment
b | Plumbing payment
c | Electrical payment
d
e
f
g
h
I
0
main BLOCK WEEK 26 Labour break down
| Masons |  | Carpenters |  | Steel fixers |  | Casual | Security | TOTALS
| Plaster | Walling | class A | class B | class A | class B
|  |  | Talam |  | Boni | ziporah
| 1000 | 900 | 1000 | 900 | 1200 | 600 | 450 | 450
Sun | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 4
Mon | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 4
Tue | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 4
Wed | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 4
Thu | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 4
Fri | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 4
Sat | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 4
TOTAL | 0 | 0 | 7 | 0 | 7 | 7 | 0 | 7 | 28
AMOUNT (KSH)
add | [8 empty] | 0
| 0 | 0 | 7000 | 0 | 8400 | 4200 | 0 | 3150 | 22750
22750
main BLOCK WEEK 23 Summary
| Description | [7 empty] | Total
1 | Materials on site week 25 | [7 empty] | 0
2 | Undelivered Materials week 25 | [7 empty] | 0
3 | Materials schedule Week 26 | [7 empty] | 509450
4 | Sub-contracting week 26 | [7 empty] | 0
5 | Labor week 26 (approx.) | [7 empty] | 22750
6
7
8
9
10
| TOTAL | [7 empty] | 532200

## site labour
Plumbing |  | days | amount | total
1 | Zipporah 0716061415 | 7 | 600 | 4200
2 | Boni 0723552070 | 7 | 1200 | 8400
3 | Talam 0716264190 | 7 | 1000 | 7000
4 | Ole 0791827941 | 7 | 450 | 3150
5 | Other to zipporah | 7 | 450 | 3150
| total |  |  | 25900

## Electrical 01
Electrical
NO. | ITEM | [7 empty] | Amount
|  | Rate | Ground floor pointing | cost | Ground floor piping | cost | updated | Typical floor unit pointing | cost | Typical floor unit piping | cost | 4th floor floor unit pointing | cost
1 | 50mm dia conduits | 380 |  | 0 |  | 0 | 0 | 20 | 7600 |  | 2888000 | 0 | 0
2 | 32mm coupler | 20 |  | 0 |  | 0 | 100 | 250 | 5000 |  | 100000 | 0 | 0
3 | 32mm conduit | 180 |  | 0 |  | 0 | 160 | 100 | 18000 |  | 3240000 | 200 | 36000
4 | 20mm coupler | 5 |  | 0 | 200 | 1000 | 1500 | 400 | 2000 |  | 10000 | 300 | 1500
5 | 20mm conduit | 75 |  | 0 | 100 | 7500 | 400 | 160 | 12000 |  | 900000 | 320 | 24000
6 | circular box 4-way | 25 |  | 0 | 50 | 1250 | 150 | 50 | 1250 |  | 31250 | 100 | 2500
7 | 32mm bend | 25 |  | 0 |  | 0 | 100 | 35 | 875 |  | 21875 | 100 | 2500
8 | Glue metro cement glue (tins) | 270 |  | 0 |  |  | 15 | 8 | 2160 |  | 583200 | 20 | 5400
0
1 | 25mmconduits | 140 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
2 | 25mm couplers | 7 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
3 | consumer unit 6 way 100A 240V | 1900 |  | 0 | 9 | 17100 |  | 0 | 0 |  | 0 | 0 | 0
4 | switch boxes single | 25 |  | 0 | 150 | 3750 |  | 0 | 0 |  | 0 | 0 | 0
5 | switch boxes Twin | 45 |  | 0 | 150 | 6750 |  | 0 | 0 |  | 0 | 0 | 0
6 | 50mm couplers | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
7 | 25mm bend | 30 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
8 | Elbow 50mm | 40 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
9 | DB fuse board 100A 415v original | 10000 |  | 0 | 1 | 10000 |  | 0 | 0 |  | 0 | 0 | 0
10 | MCCB |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
11 | Earth rod |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
12 | Rails |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
13 | Double pole |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
| TOTAL |  |  | 0 |  | 47350 |  |  | 48885 |  | 7774325 |  | 71900
TOTAL

## Mechanical 01
PLUMBING
| Item | Rate | Ground floor (no.) pointing | Total | Typical floor pointing | Cost | Ground floor piping | cost | Typical floor piping | cost
1 | 25mm ppr pipes | 230 |  | 0 | 0 | 0 | 40 | 9200 | 80 | 18400
2 | 25mmx1/2" ppr male sockets | 25 |  | 0 | 0 | 0 |  | 16 | 32 | 800
3 | 25mmx3/4" ppr female sockets | 30 |  | 0 | 0 | 0 |  | 16 | 32 | 960
4 | 25mmx1/2 ppr female tee | 25 |  | 0 | 0 | 0 | 8 | 200 | 16 | 400
5 | 25mmx1/2" ppr sockets | 6 |  | 0 | 0 | 0 | 35 | 210 | 70 | 420
6 | 25MM ppr elbows | 9 |  | 0 | 0 | 0 | 40 | 360 | 80 | 720
7 | 25mm ppr tee | 10 |  | 0 | 0 | 0 | 35 | 350 | 70 | 700
8 | 25mmx1/2" ppr female elbow | 25 |  | 0 | 0 | 0 | 45 | 1125 | 90 | 2250
9 | 4" pvc bend | 150 | 16 | 2400 | 0 | 0 | 8 | 1200 | 16 | 2400
10 | 4" pvc tee | 150 |  | 0 | 0 | 0 |  | 0 | 16 | 2400
11 | 4" Gulley trap | 180 | 9 | 1620 |  |  |  | 0 |  | 0
12 | 4" pvc pipe | 1200 | 10 | 12000 | 4 | 4800 | 16 | 19200 | 32 | 38400
13 | 4 way floor trap | 350 | 16 | 5600 | 32 | 11200 |  | 0 |  | 0
14 | 3" pvc bend | 100 | 8 | 800 | 0 | 0 |  | 0 |  | 0
15 | 3" pvc tee | 120 |  | 0 | 0 | 0 |  | 0 | 16 | 1920
16 | 3" pvc pipe | 700 | 8 | 5600 | 0 | 0 | 16 | 11200 | 32 | 22400
17 | 2" pvc bend | 80 | 2 | 160 | 20 | 1600 | 8 | 640 | 16 | 1280
18 | 2" pvc tee | 120 | 8 | 960 | 16 | 1920 |  | 0 |  | 0
19 | 2" pvc pipe | 580 | 4 | 2320 | 5 | 2900 | 2 | 1160 | 4 | 2320
20 | 1 1/2" pvc bend | 25 | 24 | 600 | 48 | 1200 | 16 | 400 | 48 | 1200
21 | 1 1/2" pvc pipe. | 500 | 6 | 3000 | 28 | 14000 | 3 | 1500 | 6 | 3000
22 | 3"x2" pvc r bush | 60 |  | 0 | 0 | 0 | 8 | 480 | 16 | 960
23 | 2x11/2" pcv r bush | 20 |  | 0 | 0 | 0 | 8 | 160 | 16 | 320
24 | 4x2" pvc boss connector. | 70 |  | 0 | 0 | 0 |  | 0 | 16 | 1120
25 | 3/2" gatevalve (pegler) | 680 |  | 0 | 0 | 0 |  | 8 | 16 | 10880
26 | 1/2" stopcork (cobra) | 2000 |  | 0 | 0 | 0 |  | 8 | 16 | 32000
27 | 1/2" gi hex nipples | 15 |  | 0 | 0 | 0 |  | 40 | 80 | 1200
28 | 1/2" gi cup plugs | 15 |  | 0 | 0 | 0 |  | 0 |  | 0
29 | 6" pvc pipe | 2600 | 6 | 15600 | 0 | 0 |  | 0 |  | 0
30 | Thread tapes pkts | 15 |  | 0 | 0 | 0 |  | 8 | 16 | 240
31 | storage tank | 40000 |  | 0 | 0 | 0 |  | 0 |  | 0
32 | 500ml tangit glue | 490 | 5 | 2450 | 5 | 2450 | 4 | 1960 | 8 | 3920
33 | boss white | 150 |  |  |  | 0 | 1 | 150 | 2 | 300
| TOTAL |  |  | 53110 |  | 40070 |  | 49591 |  | 150910

## Mechanical
Plumbing
NO. | ITEM | Unit | [5 empty] | on site
|  |  | No GF | No FF | TOTAL | Rate | Cost | 23.03.2018
1 | 25mm ppr pipes |  | 0 | 0 | 0 | 230 | 0 |  | 0
2 | 25mmx1/2" ppr elbow |  | 0 | 0 | 0 | 25 | 0 |  | 0
3 | 1/2" stopcork (cobra) |  | 0 | 0 | 0 | 2000 | 0 |  | 0
4 | 3/2 gatevalve (pegler) |  | 0 | 0 | 0 | 680 | 0 |  | 0
5 | 25mmx1/2" ppr male sockets |  | 0 | 0 | 0 | 25 | 0 |  | 0
6 | 25mmx3/4" ppr male sockets |  | 0 | 0 | 0 | 30 | 0 |  | 0
7 | 25mmx1/2 ppr female tee |  | 0 | 0 | 0 | 25 | 0 |  | 0
8 | 25mmx1/2" ppr sockets |  | 0 | 0 | 0 | 6 | 0 |  | 0
9 | 25MM ppr elbows |  | 0 | 0 | 0 | 9 | 0 |  | 0
10 | 1/2" gi hex nipples |  | 0 | 0 | 0 | 15 | 0 |  | 0
11 | thread tapes |  | 0 | 0 | 0 | 15 | 0 |  | 0
12 | 1/2" gi cup plugs |  | 0 | 0 | 0 | 15 | 0 |  | 0
13 | 25mm ppr tee |  | 0 | 0 | 0 | 10 | 0 |  | 0
14 | 4" pvc bend |  | 16 | 0 | 16 | 150 | 0 |  | 0
15 | 3" pvc bend |  | 16 | 0 | 16 | 100 | 0 |  | 0
16 | 2" pvc bend |  | 8 | 20 | 28 | 80 | 1600 |  | 0
17 | 11/2" pvc bend |  | 24 | 48 | 72 | 25 | 1200 |  | 0
18 | 3" pvc tee |  | 0 | 0 | 0 | 120 | 0 |  | 0
19 | 2" pvc tee |  | 8 | 16 | 24 | 120 | 1920 |  | 0
20 | 3"x2" pvc r bush |  | 0 | 0 | 0 | 60 | 0 |  | 0
21 | 2x1 1/2" pcv r bush |  | 0 | 0 | 0 | 20 | 0 |  | 0
22 | 500ml tangit glue |  | 5 | 5 | 10 | 490 | 2450 | 10 | 4900
23 | 2" pvc pipe |  | 4 | 5 | 9 | 580 | 2900 | 9 | 5220
24 | 3" pvc pipe |  | 8 | 0 | 8 | 700 | 0 |  | 0
25 | 4"pvc pipe |  | 10 | 4 | 14 | 1200 | 4800 | 12 | 14400
26 | 1 1/2" pvc pipe. |  | 6 | 28 | 34 | 500 | 14000 |  | 0
27 | 4" pvc tee |  | 0 | 0 | 0 | 150 | 0 |  | 0
28 | 6" pvc pipe |  | 9 | 0 | 9 | 2600 | 0 |  | 0
29 | 4x2" pvc boss connector. |  | 0 | 0 | 0 | 70 | 0 |  | 0
30 | storage tank |  | 0 | 0 | 0 |  | 0 |  | 0
31 | 4 way floor trap |  | 16 | 32 | 48 | 350 | 11200 | 32 | 11200
| TOTAL | [5 empty] | 40070 |  | 35720

## Electrical
Electrical
NO. | ITEM | Unit | Quantity |  |  |  | Amount | 23.02.2018
|  |  |  | Rate | Cost | unit
1 | 50mm dia conduits |  | 4 | 380 | 1520 | 20 | 7600 | 35 | 13300
2 | Glue metro cement glue (tins) |  | 8 | 270 | 2160 | 8 | 2160 | 1 | 270
3 | 32mm conduit |  | 0 | 180 | 0 | 100 | 18000 | 139 | 25020
4 | 20mm conduit |  | 170 | 75 | 12750 | 160 | 12000 | 287 | 21525
5 | circular box 4-way |  | 75 | 25 | 1875 | 50 | 1250 | 50 | 1250
6 | 32mm bend |  | 0 | 25 | 0 | 35 | 875 |  | 0
7 | 32mm coupler |  | 0 | 20 | 0 | 250 | 5000 | 250 | 5000
8 | 20mm coupler |  | 300 | 5 | 1500 | 400 | 2000 | 400 | 2000
9 | consumer unit 4 way |  | 8 | 1900 | 15200 |  | 0 |  | 0
10 | conduits 25mm |  | 30 | 140 | 4200 |  | 0 |  | 0
11 | switch boxes Twin |  | 40 | 45 | 1800 |  | 0 |  | 0
12 | Elbow 50mm |  | 2 | 40 | 80 |  | 0 |  | 0
13 | 25mm bend |  | 16 | 30 | 480 |  | 0 |  | 0
14 | switch boxes single |  | 35 | 25 | 875 |  | 0 |  | 0
15 | couplers 25mm |  | 30 | 7 | 210 |  | 0 |  | 0
16 | 50mm couplers |  | 0 | 0 | 0 |  | 0 |  | 0
17 | Metr box |  | 0 |  |  |  | 0 |  | 0
18 | MCCB |  | 0 |  |  |  | 0 |  | 0
19 | Earth rod |  | 0 |  |  |  | 0 |  | 0
20 | Rails |  | 0 |  |  |  | 0 |  | 0
21 | Double pole |  | 0 |  |  |  | 0 |  | 0
22 |  |  | 0 |  |  |  | 0 |  | 0
23 |  |  | 0 |  |  |  | 0 |  | 0
24 | [6 empty] | 0 |  | 0
25 |  |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL |  |  |  | 42650 |  | 48885 |  | 68365

## mild steel
NO. | ITEM | Unit | Quantity | Rate | Cost
1 | tube 1 1/2" x 1 1/2" | pc | 6 | 750 | 4500
2 | tube 3/4" x 3/4" | pc | 3 | 360 | 1080
3 | z bars 3/4"x 3/4" | pc | 8 | 680 | 5440
4 | welding rods | pkts | 3 | 1000 | 3000
5 | Grinding disk | pc |  |  | 0
6 | Cutting disk | pc |  |  | 0
7 | Body filler | 10Kg |  |  | 0
8 | Gray metal | 4L |  |  | 0
9 | sand paper | 5L |  |  | 0
10 | bushes 3/4 | pc |  |  | 0
11 | Downstoppers | pc |  |  | 0
12 | Rivets | pc |  |  | 0
13 | Tarpentine | pc |  |  | 0
14 | tube 3" x 3" | pc |  |  | 0
15 | Metal sheet 8x4x1.5mm thk | pc |  |  | 0
16 | flat 1" x 3/26" | pc
17 | stay pin
14020

## Sheet1
quarter 1
quarter 2 |  | category 1 | category 2 | cartype | american | japanese
quarter 3 |  | american | toyota | american | toyota | toyota
quarter 4 |  |  |  | japanese | ford | honda
nissan
| materials |  |  |  | no | material
| Marine boards |  |  |  | 1 | Marine boards
| mould oil |  |  |  | 2 | mould oil
| Electrical materials PIPING GF |  |  |  | 3 | binding wire
| cutting blades |  |  |  | 4 | cutting blades
| Plumbing materials POINTING GF |  |  |  | 5 | Plumbing materials POINTING GF
| Brc A142 |  |  |  | 6 | Electrical materials POINTING GF
| Brc A142 |  |  |  | 7 | Plumbing materials PIPING GF
| Antitermite. |  |  |  | 8 | Electrical materials PIPING GF
| Antitermite. |  |  |  | 9 | Brc A142
[5 empty] | 10 | Dpc (heavy gauge)
[5 empty] | 11 | Antitermite.
[5 empty] | 12 | Lime
[5 empty] | 13 | Masonry stones 100mm
[5 empty] | 14 | Masonry stones 200mm
[5 empty] | 15 | HARDCORE

## Sheet2
90 degrees Reinforcement_tononoka rolling mills limited
| Reinforcement (4th floor slab +columns) | [7 empty] | cost per kg | 12 mtrs bar (KG) | av. Cost per kg | %
| size |  |  |  | Unit | Quantity | Rate | Cost | [8 empty] | kens |  |  |  | corrugated | glory |  | asl |  |  |  | doshi
| D8 |  |  |  | pcs | 385 | 363 | 139755 | 0.395 | 4.74 | 76.5823 | 16% | 421.08 | 420 | 1.08 | 322.32 | 415 | 87.5527 |  | 460 | 97.0464 | 410 | 86.4979 | 430 | 90.7173 | 403 | 16% | 467.48 | 98.6245
| D10 |  |  |  | pcs | 380 | 553 | 210140 | 0.62 | 7.44 | 74.328 | 16% | 641.48 | 635 | 6.48 | 505.92 | 625 | 84.0054 |  | 685 | 92.0699 | 610 | 81.9892 | 650 | 87.3656 | 613 | 16% | 711.08 | 95.5753
| D12 |  |  |  | pcs | 94 | 794 | 74636 | 0.89 | 10.68 | 74.3446 | 16% | 921.04 | 925 | -3.96 | 726.24 | 915 | 85.6742 |  | 985 | 92.2285 | 910 | 85.206 | 950 | 88.9513 | 885 | 16% | 1026.6 | 96.1236
| D16 |  |  |  | pcs | 146 | 1419 | 207174 | 1.58 | 18.96 | 74.8418 | 16% | 1646.04 | 1640 | 6.04 | 1289.28 | 1625 | 85.7068 |  | 1750 | 92.2996 | 1630 | 85.9705 | 1680 | 88.6076 | 1573 | 16% | 1824.68 | 96.2384
| D20 |  |  |  | pcs | 20 | 2579 | 51580 | 2.47 | 29.64 | 87.0108 | 16% | 2991.64 | 2650 | 341.64 | 2015.52 | 2585 | 87.2132 |  | 2750 | 92.78 | 2600 | 87.7193 | 2900 | 97.8408 | 2456 | 16% | 2848.96 | 96.1188
[20 empty] | 4300 | #DIV/0! |  |  | 4300
[8 empty] | 683285 |  | av.price per kg | 77.4215
[17 empty] | 86 | 16% | 99.76
[5 empty] | nurbai | tononoka
| total | slab | columns | on site |  | amount
D8 | 385 | 320 | 65 | 6 |  | 363 |  | 139755
D10 | 380 | 380 | 0 | 0 |  | 553 |  | 210140
D12 | 94 | 70 | 24 | 4 |  | 794 |  | 74636
D16 | 146 | 60 | 86 | 13 |  | 1419 |  | 207174
D20 | 20 | 20 | 0 | 7 |  | 2579 |  | 51580
D25 | 0 | 0 | 0 | 0 |  | 0 |  | 0
binding | [7 empty] | 0
683285
[7 empty] | 16% | 109325.6
[7 empty] | add | 0.28
[7 empty] | total | 792610.88
| total | slab | columns | on site |  | amount
D8 | 405 | 320 | 85 | 6 |  | 363 |  | 147015 |  | 2178
D10 | 417 | 380 | 37 | 0 |  | 553 |  | 230601 |  | 0
D12 | 94 | 70 | 24 | 4 |  | 794 |  | 74636 |  | 3176
D16 | 60 | 60 | 0 | 13 |  | 1419 |  | 85140 |  | 18447
D20 | 20 | 20 | 0 | 7 |  | 2579 |  | 51580 |  | 18053
D25 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
binding | [7 empty] | 0
[8 empty] | 588972 |  | 41854
|  |  | 86 | 1640 | 141040 |  | 16% | 94235.52 |  | 6696.64
| nurbai | ton |  |  |  |  | add | 0.28
d8 | 420 | 421.08 | -1.08 |  |  |  | total | 683207.8 |  | 48550.64
d10 | 635 | 641.48 | -6.48
d12 | 925 | 921.04 | 3.96 |  |  |  | paid | 683285 | 0.1396
d16 | 1640 | 1646.04 | -6.04
d20 | 2650 | 2991.64 | -341.64 |  |  |  |  | 77.2
d25 | 4150 | 0 | 4150