## Schedules
Proposed Laiser Place Apartments on L.R. No. Ngong/Ngong/30165
PROJECT INFORMATION
Total Contract Sum |  |  | : Ksh. 90,000,000
Contract Start Date |  |  | : 29th September, 2016
Site Handover |  |  | : 28th November, 2016
Contract Completion Date |  |  | : 20th January, 2018
Contract Period |  |  | : 60 Calendar Weeks
BLOCK A
Block A Sum |  |  | 40000000
Contract Period Elapsed |  |  | 52 | [5 empty] | 60
Contract Period Elapsed % |  |  | 86.67%
Gross Valuation to Date |  |  | 52781753
Gross Valuation to Contract Sum % |  |  |  | 132%
BLOCK B
Block B Sum |  |  | 40000000
Contract Period Elapsed |  |  | 32
Contract Period Elapsed % |  |  | 53.33%
Gross Valuation to Date |  |  | 19388710
Gross Valuation to Contract Sum % |  |  |  | 48.47%
WEEK 33/53: FRI, 02ND DECEMBER 2017 SITE MINUTES
present |  | John | Too | bore
Lead | Action points
KEY DATES (BLOCK A FINISHES)
Start | End | Description of Works | [5 empty] | Elements
1900-12-04 | 2017-12-07 | 1st flr tile/wood/electrical/glass works | [5 empty] | 6
2017-12-08 | 2017-12-12 | 5th flr sanitary/paint works (wood/tile/elec/glass snagging) | [5 empty] | 6
2017-12-13 | 2017-12-16 | 4th flr sanitary/paint works (wood/tile/elec/glass snagging) | [5 empty] | 6
2017-12-18 | 2017-12-21 | 3rd flr sanitary/paint works (wood/tile/elec/glass snagging) | [5 empty] | 6
BLOCK A WEEK 54 (04TH - 09TH DECEMBER) WORK SCHEDULE
Mon | (1ST FLR) wood/tile/electrical/glass works
Tue | (1ST FLR) wood/tile/electrical/glass works
Wed | (1ST FLR) wood/tile/electrical/glass works
Thur | (1ST FLR) wood/tile/electrical/glass works
Fri | (5TH FLR) paint/sanitary work (wood/tile/elec/glass snagging)
Sat | (5TH FLR) paint/sanitary work (wood/tile/elec/glass snagging)
BLOCK A WEEK 55 (11TH - 16TH DECEMBER) WORK SCHEDULE
Mon | (5TH FLR) paint/sanitary work (wood/tile/elec/glass snagging)
Tue | (5TH FLR) paint/sanitary work (wood/tile/elec/glass snagging)
Wed | (5TH FLR) paint/sanitary work (wood/tile/elec/glass snagging)
Thur | (4TH FLR) paint/sanitary work (wood/tile/elec/glass snagging)
Fri | (4TH FLR) paint/sanitary work (wood/tile/elec/glass snagging)
Sat | (4TH FLR) paint/sanitary work (wood/tile/elec/glass snagging)
BLOCK B WEEK 34 (4TH - 9TH DECEMBER) WORK SCHEDULE
Mon | 3rd flr hacking & screeding, 5th flr door/window frames, 5th flr & Exterior plaster
Tue | 3rd flr hacking & screeding, 5th flr door/window frames, 5th flr & Exterior plaster
Wed | 3rd flr hacking & screeding, 5th flr door/window frames, 5th flr & Exterior plaster
Thur | 3rd flr hacking & screeding, 5th flr door/window frames, 5th flr & Exterior plaster
Fri | 3rd flr hacking & screeding, 5th flr door/window frames, 5th flr & Exterior plaster
Sat | 3rd flr hacking & screeding, 5th flr door/window frames, 5th flr & Exterior plaster
BLOCK B WEEK 35 (11TH - 16TH DECEMBER) WORK SCHEDULE
Mon | 4th flr hacking & screeding, exterior plaster
Tue | 4th flr hacking & screeding, exterior plaster
Wed | 4th flr hacking & screeding, exterior plaster
Thur | 4th flr hacking & screeding, exterior plaster
Fri | 4th flr hacking & screeding, exterior plaster
Sat | 4th flr hacking & screeding, exterior plaster
MATERIALS ON SITE WEEK 33/53
BLOCK A
ITEM |  |  |  |  | Unit | Quantity | Rate | Cost
BLOCK B
ITEM |  |  |  |  | Unit | Quantity | Rate | Cost
Cement |  |  |  |  | bags | 142 | 580 | 82360
Sand |  |  |  |  | tonnes | 18 | 1800 | 32400
SWIMMING POOL AREA
Cement |  |  |  |  | bags | 192 | 580 | 111360
Ballast |  |  |  |  | tonnes | 60 | 1900 | 114000
Sand |  |  |  |  | tonnes | 18 | 1800 | 32400
Reinforcement bars
|  | T8 |  |  | pcs | 19 | 375 | 7125
|  | T10 |  |  | pcs | 55 | 575 | 31625
|  | T16 |  |  | pcs | 11 | 1460 | 16060
|  | T20 |  |  | pcs | 7 | 2350 | 16450
|  | T25 |  |  | pcs | 2 | 3700 | 7400
ON SITE BLOCK A & B | [7 empty] | 451180
UNDELIVERED MATERIALS WEEK 33/53
ITEM |  |  |  |  | Unit | Quantity | Rate | Cost
BLOCK A
Sanitary fittings |  |  |  |  | no. | 1 | 700000 | 700000
Cabbro |  |  |  |  | SQM | 360 | 1400 | 504000
Compacting plate hire |  |  |  |  | no. | 1 | 30000 | 30000
Roof wall water proofing |  |  |  |  | no. | 1 | 67000 | 67000
Window locks (1st flr) R-15 L-15 |  |  |  |  | no. | 30 | 200 | 6000
Window Cills (8x6) |  |  |  |  | pairs | 30 | 75 | 2250
6' Paint brush |  |  |  |  | no. | 6 | 350 | 2100
4' Paint brush |  |  |  |  | no. | 6 | 250 | 1500
Main door locks |  |  |  |  | no. | 4 |  | 0
BLOCK B
Floor tiles (7503) |  |  |  |  | no. | 1060 | 1344 | 1424640
Wall tiles (5501) |  |  |  |  | no. | 395 | 1191 | 470445
Interior windows |  |  |  |  | no. | 1 | 150000 | 150000
SWIMMING POOL/BOUNDARY WALL
3" Ordinary nails |  |  |  |  | bags | 1 | 4500 | 4500
4" Ordinary nails |  |  |  |  | bags | 1 | 4500 | 4500
Binding wire |  |  |  |  | no | 6 | 2300 | 13800
UNDELIVERED WEEK 33/53 TOTAL | [7 empty] | 3380735
MATERIAL SCHEDULE WEEK 34/54
BLOCK A
ITEM | Description |  |  |  | Unit | Quantity | Rate | Cost
Coping 600x300mm |  |  |  |  | no. | 200 | 160 | 32000
Sanding sealer |  |  |  |  | no. | 1 | 500 | 500
Tupac clear varnish |  |  |  |  | no. | 1 | 500 | 500
Aluminium corner strips |  |  |  |  | no. | 54 | 200 | 10800
Pool tiles |  |  |  |  | no. | 100 | 1344 | 134400
Granito tiles (6643) |  |  |  |  | no. | 5 | 1800 | 9000
Metal work |  |  |  |  | no. | 1 | 31250 | 31250
Labor approximation (Block A) |  |  |  |  | no. |  |  | 142150
WEEK 54 (BLOCK A) TOTAL | [7 empty] | 360600
BLOCK B
ITEM | Description |  |  |  | Unit | Quantity | Rate | Cost
Cement |  |  |  |  | bags | 200 | 580 | 116000
Plumbing works |  |  |  |  | no. | 1 | 17460 | 17460
Mixer/Generator/Vibrator fuel |  |  |  |  | lt | 5 | 85 | 425
Labor approximation (Block B) |  |  |  |  | no. |  |  | 182700
WEEK 34 (BLOCK B) TOTAL | [7 empty] | 316585
SWIMMING POOL/BOUNDARY WALL
ITEM | Description |  |  |  | Unit | Quantity | Rate | Cost
Cement |  |  |  |  | bags | 200 | 580 | 116000
Labor approximation (Swimming Pool/Boundary W.) |  |  |  |  | roll | 1 | 100000 | 100000
SWIMMING POOL/BOUNDARY WALL | [7 empty] | 216000
UNDELIVERED WEEK 33/53 TOTAL | [7 empty] | 3380735
WEEK 54 (BLOCK A) TOTAL | [7 empty] | 360600
WEEK 34 (BLOCK B) TOTAL | [7 empty] | 316585
SWIMMING POOL/BOUNDARY WALL | [7 empty] | 216000
TOTAL | [7 empty] | 4273920

## Labor (Block A)
BLOCK A LABOR BREAKDOWN WEEK 46
Date | Masons |  | Carpenters |  | Steel fixers |  | Casual | Security | Harry | John | TOTALS
| Plaster | Walling | class A | class B | class A | class B
| 1000 | 900 | 1000 | 900 | 1000 | 900 | 450 | 450 | 600 | 2500
Sun | [7 empty] | 1 |  |  | 1
Mon | [6 empty] | 2 | 1 | 1 | 1 | 5
Tue | [6 empty] | 2 | 1 | 1 | 1 | 5
Wed | [6 empty] | 2 | 1 | 1 | 1 | 5
Thu | [6 empty] | 2 | 1 | 1 | 1 | 5
Fri | [6 empty] | 2 | 1 | 1 | 1 | 5
Sat | [6 empty] | 2 | 1 | 1 | 1 | 5
TOTAL PER CATEGORY | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 7 | 6 | 6 | 31
AMOUNT (KSH) | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 3150 | 3600 | 15000 | 27150
ELECTRICAL CONTRACT
MECHANICAL CONTRACT
CASTING CONTRACT
PAINTWORK | [10 empty] | 30000 | rate | pay | retain
TILE WORK | [10 empty] | 30000 | 18 | 15 | 3
METAL WORK CONTRACT | [10 empty] | 10000
WOOD WORK CONTRACT | [10 empty] | 40000
GLASS WORK CONTRACT | [10 empty] | 5000
WATER PROOFING WORK CONTRACT
TOTAL | [10 empty] | 142150

## Labor (Block B)
BLOCK B LABOR BREAKDOWN WEEK 26
Date | Masons |  | Carpenters |  | Steel fixers |  | Casual | Security | Harry | John | TOTALS
| Plaster | Walling | class A | class B | class A | class B
| 1000 | 900 | 1000 | 900 | 1000 | 900 | 450 | 450 | 600 | 2500
Sun | [10 empty] | 0
Mon | 10 | 7 | 1 | 4 | 1 | 2 | 15 |  |  |  | 40
Tue | 10 | 7 | 1 | 4 | 1 | 2 | 15 |  |  |  | 40
Wed | 10 | 7 | 1 | 4 | 1 | 2 | 15 |  |  |  | 40
Thu | 10 | 7 | 1 | 4 | 1 | 2 | 15 |  |  |  | 40
Fri | 10 | 7 | 1 | 4 | 1 | 2 | 15 |  |  |  | 40
Sat | 10 | 7 | 1 | 4 | 1 | 2 | 15 |  |  |  | 40
TOTAL PER CATEGORY | 60 | 42 | 6 | 24 | 6 | 12 | 90 | 0 | 0 | 0 | 240
AMOUNT (KSH) | 60000 | 37800 | 6000 | 21600 | 6000 | 10800 | 40500 | 0 | 0 | 0 | 182700
ELECTRICAL CONTRACT
MECHANICAL CONTRACT
CASTING CONTRACT
SEPTIC CONTRACT | [11 empty] | rate | pay | retain
TILE WORK | [11 empty] | 18 | 15 | 3
METAL WORK CONTRACT
WOOD WORK CONTRACT
TOTAL | [10 empty] | 182700

## Labor Tracking (Block A)
BLOCK A LABOR TRACKING
Date | Masons |  | Carpenters |  | Steel fixers |  | Casual | Security | Harry | John | TOTALS |  | Daily
| Plaster | Walling | class A | class B | class A | class B
| 1000 | 900 | 1200 | 900 | 1200 | 900 | 450 | 450 | 600 | 2500
Sun | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 1 | 0 | 7 |  | 3300
Mon | 12 | 1 |  | 1 |  |  | 30 | 1 | 1 |  | 46 |  | 28350
Tue | 13 | 1 |  | 1 |  |  | 27 | 1 | 1 |  | 44 |  | 28000
Wed | 14 | 1 |  |  |  |  | 26 | 1 | 1 | 1 | 44 |  | 30150
Thu | 14 | 1 |  |  |  |  | 38 | 1 | 1 | 1 | 56 |  | 35550
Fri | 9 | 1 | 1 | 4 | 1 | 1 | 24 | 1 | 1 | 1 | 44 |  | 31150 |  |  | Casual
Sat | 8 | 1 | 1 | 4 | 1 | 1 | 25 | 1 | 1 | 1 | 44 |  | 30600 |  |  | John | 15000
Welder
TOTAL PER CATEGORY | 70 | 6 | 2 | 10 | 2 | 2 | 175 | 7 | 7 | 4 | 285 |  |  |  |  | Mwakina
15000
AMOUNT (KSH) | 70000 | 5400 | 2400 | 9000 | 2400 | 1800 | 78750 | 3150 | 4200 | 10000 | 187100 |  | 187100 | 31183.3333
ELECTRICAL CONTRACT
MECHANICAL CONTRACT
CASTING CONTRACT
SEPTIC CONTRACT
TILE WORK | [10 empty] | 12900
METAL WORK CONTRACT | [10 empty] | 5000
WOOD WORK CONTRACT | [10 empty] | 10000
TOTAL | [10 empty] | 215000
BLOCK A
WOOD WORK (MWAKINA) |  |  |  | TOTALS |  | JOB DONE |  |  |  | TILE WORK |  |  | TOTALS | JOB DONE
22 04 2017 | 3200 |  |  | 3200 | [5 empty] | 26 06 2017 |  | 1500
29 04 2017 | 4800 | 600 |  | 5400 | [5 empty] | 01 07 2017 |  | 7200 | 8700 | [5 empty] | 19800
06 05 2017 | 7200 | 3600 | 2400 | 13200 | [5 empty] | 08 07 2017 |  |  | 12900 | [5 empty] | 1200 | 5 | 6000
13 05 2017 | 7200 | 7200 |  | 14400 | [5 empty] | 13 07 2017 |  | 1000 | [6 empty] | 450 | 5 | 2250
20 05 2017 | 4800 | 3450 |  | 8250 | [5 empty] | 15 07 2017 |  | 16100 | 17100
27 05 2017 | 7200 |  |  | 7200 | [5 empty] | 22 07 2017 |  |  | 17100
03 06 2017 | 7200 |  |  | 7200 | [5 empty] | 29 07 2017 |  |  | 19800
10 06 2017 | 7200 |  |  | 7200 | [5 empty] | 05 08 2017 |  |  | 39800 |  | 19800 | 20000
17 06 2017 |  |  |  | 10000 | [5 empty] | 15 08 2017 |  |  | 1000
24 06 2017 |  |  |  | 10000 | [5 empty] | 19 08 2017 |  |  | 19800
01 07 2017 |  |  |  | 10000 | [5 empty] | 26 08 2017 |  |  | 19800
08 07 2017 |  |  |  | 10000 | [5 empty] | 01 09 2017 |  |  | 500
15 07 2017 |  |  |  | 10000 | [5 empty] | 02 09 2017 |  |  | 39500 | [7 empty] | 1050
22 07 2017 |  |  |  | 4800 | [5 empty] | 07 09 2017 |  | machine/cable | 7850 | [7 empty] | 6800
[10 empty] | 09 09 2017 |  |  | 28050
[10 empty] | 16 09 2017 |  |  | 31350
[10 empty] | 23 09 2017 |  |  | 34500
[10 empty] | 30 09 2017 |  |  | 38250
[5 empty] | LOSS | -7750 |  |  |  | 07 10 2017 |  |  | 39600
[10 empty] | 14 10 2017 |  |  | 37200
[10 empty] | 21 10 2017 |  |  | 13200
[10 empty] | 04 11 2017 |  |  | 15600
[10 empty] | 11 11 2017 |  |  | 24300
110000
TOTALS |  |  |  | 120850 |  | 113100 |  |  |  | TOTALS |  |  | 465900 | 416580 |  |  | 500
1600
1000000 |  |  |  | 879150 |  | 886900 |  |  |  | 410940 |  |  | -54960 | -5640 |  |  | 1000
[14 empty] | -49320 |  |  | 168055
[17 empty] | 136200 | 31855
WOOD WORK |  |  |  | TOTALS |  | JOB DONE
05 08 2017 |  |  |  | 15000
19 08 2017 |  |  |  | 18000
26 08 2017 |  |  |  | 20000
02 09 2017 |  |  |  | 80000
09 09 2017 |  |  |  | 35000
16 09 2017 |  |  |  | 35000
23 09 2017 |  |  |  | 10000
30 09 2017 |  |  |  | 30000
07 10 2017 |  |  |  | 40000
14 10 2017 |  |  |  | 35000
21 10 2017 |  |  |  | 30000
30 10 2017 |  |  |  | 20000
04 11 2017 |  |  |  | 30000
11 11 2017 |  |  |  | 40000
TOTALS |  |  |  | 438000 |  | 471500
33500
PAINT WORKS |  |  |  | TOTALS |  | JOB DONE
28 08 2017 |  |  |  | 5000
01 09 2017 |  |  |  | 9000
09 09 2017 |  |  |  | 38000
16 09 2017 |  |  |  | 74000
23 09 2017 |  |  |  | 75000
30 09 2017 |  |  |  | 79000
07 10 2017 |  |  |  | 40000
14 10 2017 |  |  |  | 54000
21 10 2017 |  |  |  | 20000
04 11 2017 |  |  |  | 30000
11 11 2017 |  |  |  | 5000
TOTALS |  |  |  | 429000 |  | 434500
5500
GLASS WORKS |  |  |  | TOTALS |  | JOB DONE
19 09 2017 |  |  |  | 5000
04 11 2017 |  |  |  | 25000
11 11 2017 |  |  |  | 10000
TOTALS |  |  |  | 40000 |  | 100000
60000

## Labor Tracking (Block B)
BLOCK B LABOR TRACKING
Date | Masons |  | Carpenters |  | Steel fixers |  | Casual | Security | Harry | John | TOTALS | Daily
| Plaster | Walling | class A | class B | class A | class B
| 1000 | 900 | 1200 | 900 | 1200 | 900 | 450 | 450 | 600 | 2500
Sun | [10 empty] | 0 | 0
Mon |  | 1 | 1 | 7 | 1 | 4 | 14 |  |  |  | 28 | 19500
Tue |  | 1 | 1 | 7 | 1 | 4 | 19 |  |  |  | 33 | 21750
Wed |  | 1 | 1 | 7 | 1 | 1 | 20 |  |  |  | 31 | 19500
Thu |  | 1 | 1 | 1 | 1 | 1 | 7 |  |  |  | 12 | 8250
Fri |  | 2 |  | 1 |  |  | 7 |  |  |  | 10 | 5850
Sat |  | 5 |  | 1 |  |  | 7 |  |  |  | 13 | 8550 |  |  | Casual
John
TOTAL PER CATEGORY | 0 | 11 | 4 | 24 | 4 | 10 | 74 | 0 | 0 | 0 | 127 |  |  |  | Welder
Mwakina
AMOUNT (KSH) | 0 | 9900 | 4800 | 21600 | 4800 | 9000 | 33300 | 0 | 0 | 0 | 83400 | 83400 |  | 13900 |  | 0
ELECTRICAL CONTRACT
MECHANICAL CONTRACT
CASTING CONTRACT
SEPTIC CONTRACT
METAL WORK CONTRACT
WOOD WORK CONTRACT
[17 empty] | John | Too
TOTAL | [10 empty] | 83400 |  | 151800 |  | Total | A | 202050 | 215000
[13 empty] | 15000 |  |  | B | 136350 | 83400
7350
[13 empty] | 10000 |  |  | Grand | 338400 | 298400
12900
[13 empty] | 5000 |  |  | Difference |  | 40000
202050
83400
215000
80000
39500
417900