        PROGRESS REPORT ON PRODUCT DEVELOPMENT (INVENTORY)

        FOR THE PERIOD AUGUST 12TH – OCT 2ND, 2018

        BY:
        BY SOLOMON NYEFENE (CPO)

Table Of Content
0.1 Introduction
0.2 General Task Overview
0.3 General Task Schedule
0.4 Individual Assignments
0.5 Individual Progress
0.6 General progress
0.7 Progress vrs time

0.1 INTRODUCTION

       Following our target users needs as clearly demonstrated in the numerous feedback we have gathered during sales attempts of the existing product (BidiiBuild Project Management), and as it was initial envisioned, we took to a better direction to make BidiiBuild an easy to sell and a value-packed product through the addition of a robust Inventory Management System and a retouch to the existing product with the addition of extra modules and functionalities. The quantum of tasks required to achieve this goal within set time lines necessitated hiring of two extra developers to assisted with the front end task. This report brings to light a summary of the general task, general task schedule, individual task schedules, individual progress and the general progress as at 30th September 2018.

0.2 THE GENERAL TASK

 As hinted in the introduction, we embarked on a broader goal to have a fully functional Inventory Management System and the addition of Daily Logs and Cost Tracking capabilities to to the existing product. This Goal has been scheduled for execution in two phases

 Phase 1 (August 10th – October, 10th 2018): A fully functional Inventory Management System

 Phase 2 (October 10th – November 15th, 2018) : Addition of Daily Logs and Cost Tracking functionalities to the existing product .

In all, the entire project is expected to be delivered before November 15th, 2018

0.3 INDIVIDUAL ASSIGNMENTS
The project is being executed by a dev team of 4, one back end and three front end.

       Task assignments
 0.3.1 Joe Abokpoe (CTO): Back end development
        Joe has been tasked to make available the API end points to be consumend by the front end. , user account creation, authentication and authorization and their associated logics and functionalities. He also holds the task to coordinate all dev activities

0.3.2 Nyefene Solomon (CPO) : Front end development
Solomon has been task to ensure that a user will be able to ;

TASK	STATUS
View a list of all products/mats	READY
Add a new product/material	READY
Delete product/material,	READY
Update details of product/mat	READY
Sort the existing products/mat...	READY
Filter products/materials list	READY
Mark products/mats as active	READY
Import products/materials	NOT READY
Export products/materials	NOT READY

PERCENTAGES	COMPLETED	REMAINING
	78%	22%

EQUIPMENT

TASK	STATUS
View a list of all equipment	READY
Add a new equipment	READY
Delete an equipment	READY
Update details of equipment	READY
Sort equipment list	READY
Filter equipment list	READY
Mark as operational or not	READY
Import equipment	NOT READY
Export equipment	NOT READY

PERCENTAGES	COMPLETED	REMAINING
	78%	22%

SUPPLIERS

TASK	STATUS
View all suppliers	READY
Add new supplier	READY
Delete supplier(s)	READY
Update supplier	READY
Sort suppliers	READY
Filter suppliers	READY
Mark supplier as active	READY
Import suppliers	NOT READY
	NOT READY

PERCENTAGES	COMPLETED	REMAINING
	78%	22%

0.3.2 Itunu (Hire) : Front end development
Itunu has been tasked to ensure a user is able to ;

TASK	STATUS
View a list of all purchase orders	READY
Add a new purchase order	READY
Delete a purchase order	READY
Update a purchase order	READY
Sort the sort purchase orders	READY
Filter purchase orders	READY
Mark	READY
Import products/materials	NOT READY
Export products/materials	NOT READY

PERCENTAGES	COMPLETED	REMAINING
	78%	22%

        02/01/2018

The Manager
Menzgold
East Legon Branch

        AUTHORIZATION LETTER
Due to my busy schedule, I will not be able to come personally for the dividend on my investment (Ghc2,400) which was due on the 27h of September, 2018.
I herein authorise that this (dividend) be paid to the bearer (Madam Danso Abena Patience of this note on my behalf.

Kindly find below relevant information for your processing

Account number:
Account Name: Solomon Nyefene Daboni
Contact: 024 85 77 295

For further clarification, kindly contact me.

Thank you